Household Mapping and Listing Tool for Verbal Autopsy Study

# Data Completeness Report

|  |  |
| --- | --- |
| Study Title | HouseholdMapping |
| Chief Investigator Name: | Professor Bosede Afolabi |
| Co-Investigators: | Dr. Aduragbemi Banke-Thomas, Dr. Adeyemi Adebola Okunowo, Dr. Victoria Omoera, Dr. Ladi Abudu, Dr. Veronica Iwayemi, Prof. Ololade Wright, Dr. Adedoyin Ogunyemi, Dr. Fatimat Motunrayo Akinlusi, Dr. Donald Imosemi, Dr. Oluchi Kanma-Okafor |
| Report Date: | 27 March, 2024 |
| Prepared by: | Hameed Adelabu; Ndubuisi Ezumezu |

Other Key Data Statistics Completeness

| **Data Items** | **Expected No.** | **Actual No.** | **Percentage** |
| --- | --- | --- | --- |
| Total number of building |  | 11,005 |  |
| Geolocation | 11005 | 10,891 | 99 |
| Total No. of households |  | 33,472 |  |
| About the household | 33472 | 28,022 | 84 |
| Pregnant women | 984 | 779 | 79 |
| Maternal death | 175 | 13 | 7 |
| Stillbirth | 78 | 60 | 77 |
| Dates entered for exp. delivery | 779 | 726 | 93 |
| Dates entered for maternal death | 13 | 5 | 38 |
| Dates entered for stillbirth | 60 | 59 | 98 |

Household done per LGA

| **LGA** | **EAs** | **Households Expected** | **Household Done** | **Household Balance** | **\*Est Days Required** |
| --- | --- | --- | --- | --- | --- |
| Ibeju-Lekki | 10 | 800 | 1,127 | -327 | 0 |
| Alimosho | 33 | 2,640 | 3,533 | -893 | -1 |
| Badagry | 9 | 720 | 1,077 | -357 | -5 |
| Somolu | 8 | 640 | 914 | -274 | 0 |
| Lagos Mainland | 17 | 1,360 | 1,552 | -192 | -2 |
| Agege | 19 | 1,520 | 2,125 | -605 | -2 |
| Surulere | 10 | 800 | 856 | -56 | -1 |
| Oshodi-Isolo | 10 | 800 | 1,162 | -362 | 0 |
| Lagos Island | 7 | 560 | 601 | -41 | -1 |
| Mushin | 10 | 800 | 1,283 | -483 | 0 |
| Ajeromi | 15 | 1,200 | 1,480 | -280 | -3 |
| Kosofe | 10 | 800 | 863 | -63 | -1 |
| Amuwo odofin | 21 | 1,680 | 1,768 | -88 | -1 |
| Epe | 10 | 800 | 1,143 | -343 | 0 |
| Ikeja | 8 | 640 | 640 | 0 | 0 |
| Ikorodu | 14 | 1,120 | 2,028 | -908 | -7 |
| Apapa | 17 | 1,360 | 1,732 | -372 | -2 |
| Ojo | 10 | 800 | 1,277 | -477 | -6 |
| Eti-Osa | 10 | 800 | 903 | -103 | 0 |
| Ifako-Ijaiye | 14 | 1,120 | 1,958 | -838 | -6 |
| Grand Total | 262 | 20,960 | 28,022 | -7,062 |  |

\*Please note: Alimosho (4 Groups Expected), Agege (2 Groups Expected), Apapa (2 Groups Expected), Epe (needs to update before we determine).

Daily Expected vs. Actual Household

| Mapping Day | Day | Daily Mapping (expected) | Daily Mapping (actual) | Cumulative Mapping (expected) | Cumulative Mapping (actual) |
| --- | --- | --- | --- | --- | --- |
| 1 | Day 1 | 1,048 | 611 | 1,048 | 611 |
| 2 | Day 2 | 1,048 | 828 | 2,096 | 1,439 |
| 3 | Day 3 | 1,048 | 874 | 3,144 | 2,313 |
| 4 | Day 4 | 1,048 | 1,036 | 4,192 | 3,349 |
| 5 | Day 5 | 1,048 | 977 | 5,240 | 4,326 |
| 6 | Day 6 | 1,048 | 537 | 6,288 | 4,863 |
| 7 | Day 7 | 1,048 | 1,026 | 7,336 | 5,889 |
| 8 | Day 8 | 1,048 | 1,337 | 8,384 | 7,226 |
| 9 | Day 9 | 1,048 | 1,377 | 9,432 | 8,603 |
| 10 | Day 10 | 1,048 | 1,555 | 10,480 | 10,158 |
| 11 | Day 11 | 1,048 | 1,426 | 11,528 | 11,584 |
| 12 | Day 12 | 1,048 | 2,434 | 12,576 | 14,018 |
| 13 | Day 13 | 1,048 | 1,325 | 13,624 | 15,343 |
| 14 | Day 14 | 1,048 | 2,236 | 14,672 | 17,579 |
| 15 | Day 15 | 1,048 | 1,975 | 15,720 | 19,554 |
| 16 | Day 16 | 1,048 | 1,506 | 16,768 | 21,060 |
| 17 | Day 17 | 1,048 | 1,567 | 17,816 | 22,627 |
| 18 | Day 18 | 1,048 | 1,411 | 18,864 | 24,038 |
| 19 | Day 19 | 1,048 | 1,552 | 19,912 | 25,590 |
| 20 | Day 20 | 1,048 | 1,021 | 20,960 | 26,611 |
| 21 | Day 21 | 1,048 | 1,098 | 22,008 | 27,709 |
| 22 | Day 22 | 1,048 | 246 | 23,056 | 27,955 |
| 23 | Day 23 | 1,048 | 67 | 24,104 | 28,022 |

